## Work Plan
Updated UK EITI Work plan - June 2018
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2018/19 | 2019/20 | 2020/21 | 2021/22
1. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources. | Precondition - Functions legislation to allow HMRC to engage in EITI. | 1. Lack of awareness on the extractive industries in the UK. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.1 Hold post-validation outreach event to provide stakeholders with an update on progress & restate UK's commitment to EITI. Possible Ministerial attendance. | Event aimed at communicating with a wider audience. | Increase awareness and support for UK implementation of EITI in the UK. | UK MSG & UK EITI Secretariat. | 2019-04-01 |  | 2000 |  |  | Pending
|  | 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.2 Use range of communications channels to ensure that all companies within scope of UK EITI are aware of the need to report. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | July/August 2018 |  |  |  |  | On-going
|  | 3. Current inconsistent production of data. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.3 Improve guidance and templates to help in-scope companies report under EITI. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible webinar event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | July/August 2018 |  |  |  |  | On-going
|  | 4. Lack of awareness of EITI. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.4 Independent administrator to hold workshops with companies in scope of UK EITI to explain how to complete the reporting templates. | Workshops for oil & gas and mining & quarrying companies - venue tbc. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-03-01 | 1000 |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Scoping study into implementation of online disclosure (mainstreaming). | Scoping study by BEIS analysts in consultation with MSG members. | The UK EITI is disclosed as soon asc practically possible through continuous online disclosure. | UK MSG & UK EITI Secretariat. | Jul-Sept 18 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.6 Independent administrator to collect information from government and companies for reconciliation | Complete reconciliation. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator, HMRC, Coal Authority, Oil and Gas Authority, The Crown Estate, Crown Estate Scotland, UK MSG & UK EITI Secretariat. | July/August 2018 |  |  |  |  | On-going
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.7 Review and agree the scope and methodology for the 2017 reconciliation process. | Meeting of reconciliation subgroup. | An agreed methodology for the 4th UK EITI report. | UK MSG & UK EITI Secretariat. | 2018-07-01 |  |  |  |  | Pending
2. Ensure information is readily accessible and presented to the public in a clear manner | Precondition- All stakeholders need to be engaged on EITI and need to have a good understanding of the extractives industry on the UK - Need an informed and engaged MSG -Expertise needed on presentation of the data | 1. Lack of awareness on the extractive industries in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.1 Ensure that EITI website is updated in a timely manner to provide relevant information | UK EITI website updated when there are changes in MSG membership and new documents to upload. | Valuable information source for stakeholders leading to increased understanding and awareness of UK EITI. | UK EITI Secretariat | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.2 Use MSG members to ensure that the report content is accessible to multiple audiences | UK EITI website updated and the annual report is available in accessible format as required by the Gov.UK website. | Maximise audience of EITI report and comply with Gov.UK regulations. | UK EITI Secretariat | Nov-Dec 2018 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.3 Ensure the report is written in plain English | Increased support and understanding amongst key stakeholder groups | Increase understanding and awareness of UK EITI and ensure messages resonate with industry, civil society and Government representatives | Sectoral subgroup, with review by MSG | July-October 2018 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.4 Consider and agree the presentation of EITI reports. Decide whether the data should be machine readable, whether information should be coded or tagged so it can be compared with other publicly available data. | Access to a range of data that can be manipulated | Increase understanding of the extractive industries in the UK and encourage debate. | UK MSG & UK EITI Secretariat | July-October 2018 |  |  |  |  | On-going
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 2.5 Independent administrator to present EITI report to the MSG to consider and endorse before publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2018-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.6 MSG to agree EITI report ahead of publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG & UK EITI Secretariat | 2018-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.7 Update the communications plan to promote the published report | Develop and update the communications plan | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | 2018-10-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.8 Publication of annual EITI report | Publish report | Report is used as a tool to improve debate on extractive industry issues | UK MSG & UK EITI Secretariat | 2018-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.9 Use MSG member networks to promote EITI report | Dissemination of the report to a wide audience | Report is used as a tool to improve debate on extractive industry issues | Communications sub group, UK MSG & UK EITI Secretariat | 2018-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.10 During outreach, consult stakeholders on how to present information e.g. would a summary report be valuable | Recommendations received during outreach activities | A record of outreach and comments received is maintained that should be reviewed regularly | Communications sub group and UK EITI Secretariat | 2018-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 2.11 Targeted communications to specific civil society groups to raise awareness of the EITI report | Increase awareness of the EITI report | Stimulate debate on the UK extractive industries | Communications sub group and UK EITI Secretariat | 2018-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.1 Monitor the need for training activities, workshops etc. for MSG members | Various training activities | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | UK MSG & UK EITI Secretariat | 2019-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.2 Invite representatives from other countries to attend MSG meetings and share UK's experience | Share experiences with colleagues overseas | Increased understanding of options to implement EITI for UK and other countries sharing good practice. | UK EITI Secretariat | 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.3 Use MSG membership to promte and stimulate interest in EITI within their industry. | MSG members to use/reference EITI in their own publications/websites and consultation responses | Increased understanding of EITI within industry and its importance to the transparency agenda | UK MSG | 2018-07-01 |  |  |  |  | On-going
3. Support the UK government’s championing of extractives transparency and open government | Precondition- The profile of EITI needs to be raised and more needs to be done to promote what the UK is doing with implementation. Reliant on all companies complying with EITI. | 1. Only budget to cover costs of report and possible launch activity around publication. 2.DFID is responsible for international influencing. 3. Lack of awareness of EITI. | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.1 Allow nominated people to attend MSG meetings | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 0 | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 4.3 Participate in EITI calls with other developed countries to share experiences | Share EITI experience with other countries via webinars organised by EITI International Secretariat. | Expand understanding of options to implement EITI for UK and other countries | UK EITI Secretariat | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.2 Company Engagement | 4.4 Consider methods to encourage good practice by companies | Disseminate information on good practice by companies | Helping to share good practice | UK MSG & UK EITI Secretariat | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 4.5 Re-engage with Civil Society Network (CSN) with view to encouraging them to return to the MSG. | Use independent mediator to work with CSN and EITI Secretariat. | The return of CSN to the MSG | Independent mediator and UK EITI Secretariat | 2019-03-01 | 2000 |  |  |  | Pending
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.6 Review the UK EITI MSG terms of reference. | Work with BEIS legal team to review current terms of reference. | More robust and relevant terms of reference | UK MSG, UK EITI Secretariat & BEIS Legal | 2019-04-01 |  |  |  |  | Pending
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.7 Review membership of the constituencies, including lengths of service and succession planning. | Work with both industry and civil society to agree updated mechanisms for appointing new MSG members and succession planning. | Ensure that the MSG has adequate membership and robust succession arrangements. Industry has agreed a plan and a process is now in place. | UK MSG, UK EITI Secretariat & BEIS Legal | April 2019 for CS |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.3 Lessons learned and follow up on recommendations | 4.8 Independent administrator to make recommendations for future reconciliation processes | Generate suggestions to improve reconciliations | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive. UK EITI to benefit from continuous improvement | Independent Administrator | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 4.9 Review outcome and impacts on EITI implementation | Lessons learned on UK EITI | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive and readily accessible to stakeholders and UK benefits from continuous improvement | UK MSG & UK EITI Secretariat | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 2: Contracts and licenses - 2.5 Beneficial Ownership | 5.1 Monitor and consider existing and upcoming transparency initiatives in the UK EG Chapter 10 Accounting Directive, Transparency Directive and Register of Beneficial Ownership | Ensure that UK EITI is consistent with other transparency initiatives | UK EITI will reflect other reporting requirements to ensure any additional requirements are proportionate. | UK Government and extractive companies in scope | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.1 Regular meetings of the MSG | Hold MSG meetings every 2 months to ensure speedy and effective implementation | Strengthen the participative multi stakeholder process of EITI and increase confidence among stakeholders | UK MSG | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.2 Assess and outline plans to address any potential capacity restraints in Government agencies, companies and civil society organisations that may be an obstacle to implementation | MSG to consider and take steps to remove capacity constraints | Ensure speedy and effective implementation | UK MSG and UK EITI Secretariat | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.5 Work Plan | 6.3 Agree and maintain and current work plan, fully coasted and aligned with the reporting and validation deadlines established by the EITI Board | Up to date UK EITI work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK EITI Secretariat and UK MSG | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 6.4 Agree and publish annual progress report | Lessons learned on UK EITI | continuous improvement | UK EITI Secretariat and UK MSG | 2018-07-01 |  |  |  |  | On-going
|  |  | Requirement 8: Compliance and deadlines for implementing countries - 8.3 EITI Validation deadlines and consequences | 6.5 Undergo independent validation for EITI compliance | Assessment of EITI implementation in the UK | UK reaches compliant status | UK MSG | Jul 18 - Jan 19 |  |  |  |  | Pending