## Work Plan
Updated UK EITI Work plan - June 2015
Key
Complete
On-going
Pending
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2013 | 2014 | 2015 | 2016
1. Increase public understanding of the social and economic impacts of the UK’s extractive industries and enrich public debate on the governance and stewardship of the UK’s oil, gas and mineral resources. | Precondition- Functions legislation to allow HMRC to engage in EITI. | 1.Lack of awareness on the extractives industry in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. 3. Current inconsistent production of data. 4.Lack of awareness on EITI. | Raising awareness of EITI - requirement 1.1 | 1.1 UK issues unequivocal statement of its intention to implement the EITI. | A statement from the UK Government committing to implement EITI in the country | Demonstrated commitment of the UK Government to implement EITI in the UK | UK Prime Minister David Cameron | 2013-05-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.2 | 1.2 HMG appoints senior individual to lead UK EITI implementation | Baroness Neville-Rolfe appointed as the EITI Champion for the UK. Former EITI Champion was Jo Swinson | To champion EITI and provide strategic leadership to the process. | UK Government | 2013-05-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3g | 1.3 Form a communications sub-group | sub-group to promote EITI & make recommendations on how to promote EITI to MSG | Maximise audience of EITI report | EITI Secretariat & members | 2014-03-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI- requirement 1.3g | 1.4 Create and develop first version of communications plan | Communications plan to be presented to MSG for agreement and then implemented | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | 2014-06-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3g | 1.5 Develop EITI website which will be used to disseminate information to wider stakeholders | Creation of an EITI website on gov.uk | To provide information on EITI to a range of audiences. This includes general information on EITI through to details of the UK MSG such as minutes from meetings. | EITI UK Secretariat | 2013-05-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3 | 1.6 The EITI Champion to issue an article in the Sunday Telegraph EITI supplement explaining the reasons that the UK has signed up to EITI | Article by the EITI Champion in the Sunday Telegraph EITI supplement | To raise awareness of EITI in the UK and increase understanding of why the UK has signed up. | EITI Champion | 2013-10-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3 | 1.7 Issue a ministerial blog following the first meeting of the Multi stakeholder group through civil society networks | EITI champion to publish a blog posted on Transparency International's website | To inform stakeholders that the MSG has been formed and has commenced work on implementation | EITI Champion | 2013-10-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3g | 1.8 Develop a UK EITI brand to increase awareness | Informative website and UK logo | Increase awareness and support for UK implementation of EITI in the UK | Communications sub group | 2014-06-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3 | 1.9 Hold launch event to raise awareness of UK's commitment to become EITI-compliant | Event with speakers and break out session. | Increase awareness and support for UK implementation of EITI in the UK | EITI UK Secretariat | 2013-07-01 | 500 |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3 | 1.10 Hold outreach events to provide stakeholders an update on progress & restate UK's commitment to EITI. Also to listen to views. | Annual event aimed at communicating with a wide audience | Increase awareness and support for UK implementation of EITI in the UK | UK MSG | Jul 2013, Nov 2014 & Apr 2016 |  | 500 | 500 | 500 | On-going
|  |  | Raising awareness of EITI - requirement 1.3 | 1.11 Hold a mining event on EITI to engage with the mining sector | Mining event-12 June at the Institute of Materials, Minerals and Mining | Increase awareness and support amongst mining stakeholders of EITI in the UK | UK MSG & UK EITI Secretariat | 2014-06-01 |  |  |  |  | Complete
|  |  | Raising awareness of EITI - requirement 1.3 | 1.12 Conduct outreach to oil, gas and mining companies about EITI implementation | Increase support and awareness of UK EITI | Gain compliance with EITI by companies in scope | UK MSG & UK EITI Secretariat | Jun 2014 onwards |  |  |  |  | On-going
|  |  | Raising awareness of EITI - requirement 1.3 | 1.13 Use range of communications channels to ensure that all companies within scope of UK EITI are aware of the need to report in 1st report | Industry guidance notes, articles in trade magazines, annual event. | Increase understanding and compliance with UK EITI. | UK MSG & UK EITI Secretariat | Jun 2014 onwards |  | 1000 |  |  | On-going
|  |  | Raising awareness of EITI - requirement 1.3 | 1.14 Use range of communications channels to ensure that all EITI companies understand how to report using the EITI template | Industry guidance notes, articles in trade magazines, annual event. | Increase industry participation in UK EITI | UK MSG & UK EITI Secretariat | May 2015 onwards |  |  |  |  | On-going
|  |  | Raising awareness of EITI - requirement 1.3 | 1.15 Independent administrator to hold workshops with companies in scope of UK EITI to explain how to complete the reporting templates. | Workshops for oil & gas companies in London and Aberdeen and mineral companies venue tbc | Increase industry participation in UK EITI | Moore Stephens & UK EITI Secretariat | 2015-07-01 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.1 | 1.16 Form contextual information sub group | recommendations to MSG on contextual information to be included in EITI Report and collecting information | ensure quality information in the annual EITI Report that provides understanding of the sector | Secretariat and sub-group members | 2013-12-01 |  |  |  |  | Complete
|  |  | Collect contextual info for EITI Report- requirement 3.2 | 1.17 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.2 | 1.18 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.2 | 1.19 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collecting information for EITI Report (contextual information) - requirement 3.2 | 1.20 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.3 | 1.21 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.3 | 1.22 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries (mining) |  | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.4 | 1.23 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.4 | 1.24 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.5 | 1.25 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect contextual info for EITI Report- requirement 3.5 | 1.26 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | 1st EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | Jun - Dec 2015 |  |  |  |  | On-going
|  |  | Collect info for reconciliation - requirement 5.2 | 1.27 Establish sub-group to consider requirements for independent administrator | recommendations on independent administrator to MSG | agreed ToR for administrator, procurement process etc. | Secretariat & sub-group members | 2014-07-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 1.28 Agree assurances to be provided by reporting entities to the independent administrator | Terms of reference must outline what information should be provided to the independent administrator by the participating companies and government entities | Improve the credibility of the data. | UK MSG & UK EITI Secretariat | 2015-01-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 1.29 Draft and agree Terms of Reference for the Independent administrator | Terms of Reference document | To ensure the reconciliation is carried out thoroughly & independent administrator understands role | UK MSG, independent administrator & UK EITI Secretariat | 2015-01-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 1.30 Reconciliation subgroup to recommend text for waiver for companies to authorise government release details of receipts to administrator for reconciliation | recommendation on text of waiver | Text of waiver to be agreed that will allow reconciliation to take place | sub-group, industry and MSG | 2015-05-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 1.31 Commence the procurement process for the independent administrator | Go out to tender | Increase confidence with stakeholders on the value of EITI | UK EITI Secretariat and relevant MSG sub group | 2015-01-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 1.32 Independent administrator to collect information from government and companies for reconciliation | Complete reconciliation | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent reconciler, HMRC, DECC & companies in scope if EITI | Jun- Nov 2015 |  | tbc | tbc | tbc | Pending
2. Ensure information is readily accessible and presented to the public in a clear manner | Precondition- All stakeholders need to be engaged on EITI and need to have a good understanding of the extractives industry on the UK - Need an informed and engaged MSG -Expertise needed on presentation of the data | 1.Lack of awareness on the extractives industry in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. 3.Lack of awareness on EITI. | How we share information - requirement 1.3 | 2.1 Ensure that EITI website is updated in a timely manner to provide relevant information | Up to date EITI website | Valuable information source for stakeholders leading to increased understanding and awareness of UK EITI. | UK EITI Secretariat | Jul 2013 onwards |  |  |  |  | On-going
|  |  | Quality control of the presentation of the report - 6.1 | 2.2 Use MSG members to ensure that the report content is accessible to multiple audiences | focused communications | Maximise audience of EITI report | MSG | 2016-01-01 |  |  |  |  | Pending
|  |  | Quality control of the presentation of the report - req 6.1 | 2.3 Ensure the report is written in plain English | Increased support and understanding amongst key stakeholder groups | Increase understanding and awareness of UK EITI and ensure messages resonate with industry, civil society and Government representatives | Communications sub group | Sep 2015 - Jan 2016 |  |  |  |  | On-going
|  |  | How we share information - req 6.2 | 2.4 Consider and agree the presentation of EITI reports. Decide whether the data should be machine readable, whether information should be coded or tagged so it can be compared with other publicly available data. | Access to a range of data that can be manipulated | Increase understanding of the extractive industries in the UK and encourage debate. | UK MSG & UK EITI Secretariat | Oct - Nov 2015 |  |  |  |  | On-going
|  |  | Quality control of the presentation of the report - req 1.3g (iv) | 2.5 Independent administrator to present EITI report to the MSG to consider and endorse before publication | EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | Independent reconciler & UK MSG | Jan - Feb 2016 |  |  |  |  | Pending
|  |  | Quality control of the presentation of the report - req 1.3g (iv) | 2.6 MSG to agree 1st EITI report ahead of publication (repeated every year) | Endorsed 1st EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG & UK EITI Secretariat | 2016-02-01 |  |  |  |  | Pending
|  |  | How we share information - req 6.1 | 2.7 Update the communications plan to promote the published report | Develop and update the communications plan | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | Oct - Dec 2015 |  |  |  |  | Pending
|  |  | How we share information req 6 | 2.8 Publication of 1st EITI report | Publish report | Report is used as a tool to improve debate on extractive industry issues | UK MSG & UK EITI Secretariat | 2016-04-01 |  |  |  |  | Pending
|  |  | How we share information - rec 6.1 | 2.9 Use MSG member networks to promote EITI report | Dissemination of the report to a wide audience | Report is used as a tool to improve debate on extractive industry issues | Communications sub group, UK MSG & UK EITI Secretariat | Apr - Jul 2016 |  |  |  |  | Pending
|  |  | How we share information - rec 1.3 | 2.10 During outreach, consult stakeholders on how to present information e.g. would a summary report be valuable | Recommendations received during outreach activities | A record of outreach and comments received is maintained that should be reviewed regularly | Communications sub group and UK EITI Secretariat | Oct - Dec 2015 |  |  |  |  | On-going
|  |  | How we share information - req 6.1 | 2.11 Targeted communications to specific civil society groups to raise awareness of the EITI report | Increase awareness of the EITI report | Stimulate debate on the UK extractive industries | Communications sub group and UK EITI Secretariat | Apr - Jul 2016 |  |  | 700 | 700 | Pending
3. Enhance accountability to the UK public on the revenues from the UK's extractive industries | Precondition- All stakeholders need to be engaged on EITI and know how to use the information that is in the EITI report to encourage debate. | 1.Lack of awareness on the extractives industry in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. 3. Current inconsistent production of data. 4.Lack of awareness on EITI. | Capacity building - req 1.3 | 3.1 HMRC presentation for the MSG on taxes under the oil and gas regime | Presentation by HMRC tax expert at a meeting of the MSG | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | HMRC representatives | 2013-12-01 |  |  |  |  | Complete
|  |  | Capacity building - req 1.3 | 3.2 International Secretariat to deliver a training workshop for MSG members on EITI | One day workshop for MSG members followed by a half day workshop in April 2015 | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | Communications sub group, UK MSG & UK EITI Secretariat | Nov 2013 - April 2015 |  |  |  |  | Complete
|  |  | Capacity building - req 1.3 | 3.3 Mining experts on MSG to give presentation on mining and aggregates in UK | Presentations by mining experts at a meeting of the MSG | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | Dr Patrick Foster (Camborne School of Mines)and Jerry McLaughlin (Mineral Products Association) | 2013-02-01 | 100 |  |  |  | Complete
|  |  | Capacity building - req 1.3 | 3.4 Invitation to Eddie Rich from the International Secretariat to attend UK MSG meetings | Standing observer slot for EITI international secretariat detailed in Terms of Reference | Increase MSG understanding of the EITI implementation process and resolve queries | International EITI Secretariat | 2013-06-01 |  |  |  |  | Complete
|  |  | Capacity building - req 1.3 | 3.5 Development of an introduction to EITI to be circulated to companies in scope of EITI | Publication of guidance notes developed with industry MSG members | Increase support and compliance with UK EITI | Communications sub group & UK EITI Secretariat | Jun - Jul 2014 |  |  |  |  | Complete
|  |  | Capacity building - req 1.3 | 3.6 Monitor the need for training activities, workshops etc. for MSG members | Various training activities | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | UK MSG & UK EITI Secretariat | Oct 2013 onwards |  |  |  |  | On-going
|  |  | Contextual information requirement 3.11 | 3.7 Decide whether a publicly available register of beneficial ownership should be maintained | Beneficial ownership included in the 1st EITI report | Increase understanding of UK extractive companies | UK MSG | 2013-02-01 |  |  |  |  | Complete
|  |  | Collecting information for EITI Report (contextual information) - requirement 3.2 | 3.8 Sub group to make a recommendation to the MSG on details to be collected on beneficial ownership |  |  |  | 2015-06-01 |  |  |  |  | Complete
|  |  | Collect contextual info for EITI Report- requirement 3.5 | 3.9 Decide whether information on revenue management should be included within contextual information | More detailed 1st EITI report | Increase understanding of UK extractive companies and stimulate debate on the extractive industries | UK MSG | Jun-Dec 2015 |  |  |  |  | On-going
|  |  | increased information into public domain - requirement 3.9 | 3.10 Clarify whether DECC's publicly available register of licences meets the requirements of EITI | More comprehensive information in the 1st EITI Report | Increase accountability of UK Government and stimulate debate on the extractive industries | Communications sub group, UK MSG & UK EITI Secretariat | Jun-Dec 2015 |  |  |  |  | On-going
|  |  | increased information into public domain - requirement 3.10 | 3.11 Update DECC Guidance to make explicit that details of all applicants for licence rounds will be published in EITI report | More comprehensive information in the 1st EITI Report | Increase accountability of UK Government and stimulate debate on the extractive industries | DECC | 2014-04-01 |  |  |  |  | Complete
|  |  | MSG Attendance | 3.12 Invite representatives from other countries to attend MSG meetings and share UK's experience | Share experiences with colleagues overseas | Increased understanding of options to implement EITI for UK and other countries sharing good practice. | UK EITI Secretariat | Dec 2013 onwards |  |  |  |  | On-going
4. Support the UK government’s championing of extractives transparency and open government | Precondition- The profile of EITI needs to be raised and more needs to be done to promote what the UK is doing with implementation. Reliant on all companies complying with EITI. | 1. No budget for EITI. 2.DFID is responsible for international influencing. | MSG Attendance | 4.1 Allow nominated people to attend MSG meetings | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | Dec 2013 onwards |  |  |  |  | On-going
|  |  | MSG Attendance | 4.2 Invite experts to MSG meetings and sub groups to provide advice | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | Dec 2013 onwards |  |  |  |  | On-going
|  |  | MSG Attendance | 4.3 Participate in EITI calls with other developed countries to share experiences | Share EITI experience with other countries | Expand understanding of options to implement EITI for UK and other countries | UK EITI Secretariat | Oct 13 onwards |  |  |  |  | On-going
|  |  | MSG Attendance | 4.4 Consider methods to encourage good practice by companies | Disseminate information on good practice by companies | Helping to share good practice | UK MSG & UK EITI Secretariat | 2015-12-01 |  |  |  |  | Pending
|  |  | Quality control and learning from experience | 4.5 Independent administrator to make recommendations for future reconciliations | Generate suggestions to improve reconciliations | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive. UK EITI to benefit from continuous improvement | Independent reconciler | Apr - Jun 2016 |  |  |  |  | Pending
|  |  | Allowing HMRC to engage in EITI | 4.6 provisions to give HMRC the "function" to engage in EITI to be included in the Infrastructure Bill | HMRC are given their role via legislation. They have a "function" set out in legislation for each activity they perform and need a "function" to engage in EITI. This it to be introduced by the Infrastructure Bill. | HMRC will be able to fully participate in EITI. | HMRC | 2015-03-01 |  |  |  |  | Complete
|  |  | Quality control and learning from experience | 4.7 Review outcome and impacts on EITI implementation | Lessons learned on UK EITI | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive and readily accessible to stakeholders and UK benefits from continuous improvement | UK MSG & UK EITI Secretariat | Apr - Jun 2016 |  |  |  |  | Pending
5. Support moves towards common global reporting standards in oil, gas and mining and promote a level playing field for business in the UK and internationally. | Precondition- All companies in scope of EITI will need to comply with the voluntary initiative | information not currently consolidated | Consistency of information | 5.1 Agree scope of EITI reporting to include technical aspects of reporting e.g. comprehensiveness and data reliability | The report will have relevant information | Reliable EITI data is produced. | UK MSG | 2015-05-01 |  |  |  |  | Complete
|  |  | Consistency of information | 5.2 Establish sub-group to consider reconciliation | recommendations on taxes to be included within UK EITI and methodology for reconciliation | Agreement of methodology and taxes for reconciliation | UK MSG | 2013-12-01 |  |  |  |  | Complete
|  |  | Consistency of information | 5.3 Agree accounting period for 1st EITI report (provisional agreement for 2014 figure to be confirmed when model for reconciliation is finalised) | Companies to report figures from a consistent reporting period to the independent administrator | Readers who can compare company information for the same period | UK MSG | 2015-01-01 |  |  |  |  | Complete
|  |  | consistency of information - requirement 5.4 | 5.4 Agree level of disaggregation for the publication of data | EITI reconciliation to be broken down to a workable level that the stakeholders would find useful. | Publish a report which includes information that stakeholders will value | UK MSG | 2015-01-01 |  |  |  |  | Complete
|  |  | Collecting information for reconciliation - requirement 5.2 | 5.5 develop template for companies to populate to initiate reconciliation process. | to allow companies to give information to administrator in correct format for reconciliation. | template to be filled in by companies reporting under EITI. | reconciliation sub-group | 2015-05-01 |  |  |  |  | Complete
|  |  | Consistency of information - requirement 5.5 | 5.6 Define taxes and revenues to be covered in the EITI report | Agree taxes necessary to meet the EITI Standard and consider value of including other taxes | Publish a report which includes information that stakeholders will value | UK MSG | Dec 2013 (Oil & Gas) May 2015 (mining and minerals) |  |  |  |  | Complete
|  |  | Consistency of information | 5.7 Monitor and consider existing and upcoming transparency initiatives in the UK EG Chapter 10 Accounting Directive, Transparency Directive & beneficial ownership | Ensure that UK EITI is consistent with other transparency initiatives | UK EITI will reflect other reporting requirements to ensure any additional requirements are proportionate. | UK Government and extractive companies in scope | Jan 2014 onwards |  |  |  |  | On-going
6. Recognise and support the principles set out in the 2013 EITI Standard | Precondition-Full engagement of stakeholders. Risk- Lack of understanding about the extractives industry in the UK. | 1.Lack of awareness on the extractives industry in the UK. 2. Information is currently not consolidated and is and published through a variety of means and agencies. 3. Current inconsistent production of data. 4.Lack of awareness on EITI. | government preparation | 6.1 Establish officials group across Government departments to prepare for the 1st MSG meeting | Creation of an officials network across Government departments | Instigate the process of bringing all relevant Government departments together to overcome obstacles to EITI implementation |  | 2013-05-01 |  |  |  |  | Complete
|  |  | government preparation | 6.2 Identify and outline plans to address any potential legal or regulatory obstacles to EITI implementation | Register of obstacles | Removal of obstacles to EITI implementation in the UK | UK EITI Secretariat | 2013-11-01 |  |  |  |  | Complete
|  |  | Commitment to EITI principles - Requirement 1.3 | 6.3 HMG commits to working with civil society and industry to implement EITI. | Strengthen the participative multi stakeholder process of EITI | Ensure UK EITI is an inclusive and collaborative process | EITI Champion | Jun 2013 onwards |  |  |  |  | Complete
|  |  | government preparation | 6.4 Create UK EITI Secretariat | Formation of UK Secretariat based in the Department for Business, Innovation & Skills (BIS) | Secretariats drive implementation throughout EITI by supporting the MSG and EITI champion, coordinating the Government's position, drafting and consulting on the EITI work plan, communicating and consulting on EITI, addressing legal barriers and coordinating Government figures for reconciliation | UK Government | 2013-05-01 |  |  |  |  | Complete
|  |  | Commitment to EITI principles - Requirement 1.3f | 6.5 Industry to select own representatives for the MSG | MSG set up with equal number for all three constituencies | Strengthen the participative multi stakeholder process of EITI | Oil & Gas UK and Confederation of British Industry (CBI) nominated representatives | Jul-Sep 2013 |  |  |  |  | Complete
|  |  | Commitment to EITI principles - Requirement 1.3f | 6.6 Coordination of Government representatives for the MSG | MSG set up with equal number constituencies | Strengthen the participative multi stakeholder process of EITI | UK EITI Secretariat invited departments to nominate representatives | Jul-Sep 2013 |  |  |  |  | Complete
|  |  | Commitment to EITI principles - Requirement 1.3f | 6.7 Civil society to select their own representatives for the MSG | MSG set up with equal number constituencies | Strengthen the participative multi stakeholder process of EITI | Publish What You Pay coordinated civil society representatives | Jul-Oct 2013 |  |  |  |  | Complete
|  |  | Requirement 1.3 | 6.8 Establish MSG consisting of Government, industry and civil society representatives to oversee implementation of UK EITI | MSG set up with equal number constituencies | Strengthen the participative multi stakeholder process of EITI | UK EITI Secretariat | 2013-10-01 |  |  |  |  | Complete
|  |  | Requirement 1.3 | 6.9 MSG to agree the Terms of Reference and decision making protocols. | Endorsed Terms of Reference published on the EITI website | Provides clarity to MSG members of MSG operations and rules and also commits MSG to EITI implementation | UK MSG | 2013-12-01 |  |  |  |  | Complete
|  |  | Requirement 1.4 | 6.10 MSG to agree UK EITI objectives that are linked to the EITI principles and reflect national priorities for the extractive industries | Endorsed EITI objectives that are detailed on the work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK MSG | 2014-05-01 |  |  |  |  | Complete
|  |  | Requirement 1.3 | 6.11 Regular meetings of the MSG | Hold MSG meetings every 2 months to ensure speedy and effective implementation | Strengthen the participative multi stakeholder process of EITI and increase confidence among stakeholders | UK MSG | Oct 2013 onwards | 150 | 400 | 450 | 500 | On-going
|  |  | Requirement 1.4 | 6.12 Assess and outline plans to address any potential capacity restraints in Government agencies, companies and civil society organisations that may be an obstacle to implementation | MSG to consider and take steps to remove capacity constraints | Ensure speedy and effective implementation | UK MSG and UK EITI Secretariat | Jun- Dec 2015 |  |  |  |  | On-going
|  |  | Requirement 1.4 | 6.13 Agree and maintain and current work plan, fully coasted and aligned with the reporting and validation deadlines established by the EITI Board | Up to date UK EITI work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK EITI Secretariat and UK MSG | Jul 2014 onwards |  |  |  |  | On-going
|  |  | Requirement 1.4 | 6.14 industry, civil society and government MSG members share work plan with their constituency and gain views in advance of candidacy application | Ensure the EITI is inclusive and takes stakeholder views on board. | Strengthen the participative multi stakeholder process of EITI and increase understanding of the extractive industries in the UK | UK MSG and UK EITI Secretariat | Jun - Jul 2014 |  |  |  |  | Complete
|  |  |  | 6.15 Apply for UK EITI candidacy | Apply for UK candidature | Implementation process for UK EITI | UK MSG | 2014-10-01 |  |  |  |  | Complete
|  |  | Requirement 7.1 | 6.16 Identify, investigate and address the cause of discrepancies in reconciliation and consider recommendations for improvement from the independent reconciler | Finding of the 1st EITI report | Improves transparency of the extractive industries sector in the UK | UK MSG | Apr - May 2016 |  |  |  |  | Pending
|  |  | Requirement 7.2 | 6.17 Agree and publish annual activity report | Lessons learned on UK EITI | continuous improvement | UK MSG | Jul 2015 and annually afterwards |  |  |  |  | On-going
|  |  |  | 6.17 Undergo independent validation for EITI compliance | Assessment of EITI implementation in the UK | UK reaches compliant status | UK MSG | 2017-04-01 |  |  |  |  | Pending