## UK EITI 2020 Workplan
UK EITI 2020 Workplan
No. | Activities | Timeline | Expected Output | Expected Outcome | Responsible Entity | Cost 2019-20 | Cost 2020-21 | Cost 2021-22 | RAG rating | Progress update
1. Uphold the principles set out in the 2019 EITI Standard and implement them in a way suitable for the UK context.
1.01 | Ensure that new requirements in the 2019 are taken into account for the 2019 reconciliation report and when developing content for the new EITI website. | 2020-12-01 | Establish new Compliance Subgroup to discuss what is required to meet 2019 Standard and record this in a tracker. Update company guidance and templates to reflect any new requirements. | Full compliance with the 2019 Standard. | Compliance Subgroup, MSG |  |  |  |  | Complete. Compliance subgroup established and has discussed what is required to meet 2019 Standard and has recorded this in the Compliance tracker. The company guidance and templates were updated to reflect any new requirements and data has been added to the sectoral pages of the new EITI website to meet requirements on gender and environmental reporting. Work on the contract disclosure requirements that come into force in January 2021 is ongoing.
1.02 | Address the corrective actions raised in the UK's first validation to ensure 'satisfactory progress' in our revalidation, which due to commence November 2020. | 2020-12-01 | Establish new Compliance Subgroup to discuss what is required to address each corrective action and capture this in a validation tracker. | Satisfactory progress in the UK's revalidation. | Compliance Subgroup, MSG |  |  |  |  | Compliance Subgroup have discussed requirements to address each corrective action and captured this in the Compliance tracker. MSG to use tracker to help their discussions on when to commence the revalidation at their meeting in November 2020.
1.03 | Review the impact of the first five years of EITI implementation and explore opportunities for enriching public debate on the governance and stewardship of the UK's oil, gas and mineral resources (VALIDATION CORRECTIVE ACTION 8) | 2020-11-01 | Report analysing the first five years of EITI implentation, with input from all constituencies, that puts forward recommendations to further strengthen the impact of EITI. | MSG, its constituencies and the wider public are more aware of the impact of EITI implementation in the UK. MSG can make informed decisions to increase the impact of EITI in the UK. | Compliance Subgroup, MSG |  |  |  |  | Review of impact paper of the first five years has been agreed by the MSG and is nearly complete and ready to upload onto the UK EITI website, pending feedback from EITI International.
1.04 | Complete annual progress report/annual review of outcomes and impact of EITI implementation. This should now include documenting the efforts to improve gender equality and social inclusion. MSG to agree on the method for doing this. | 2020-12-01 | Written assessment of the impact of EITI implementation in 2019, the lessons learned from the past year and the extent to which EITI has met its objectives. | MSG, its constituencies and the wider public are more aware of the impact of EITI implementation in the UK. MSG can make informed decisions to increase the impact of EITI in the UK and ensure that EITI implementation is beneficial to the UK. | UK MSG & UK EITI Secretariat |  |  |  |  | Drafting of the annual progress report to start in the Autumn and included in the Reconciliation and State of Industry report covering 2019. To be agreed by the MSG.
1.05 | Hold UK MSG every two months, with good representation from all constituencies. | 2020-12-01 | MSG meetings every 2 months with well-considered agendas and papers to ensure speedy and effective implementation of EITI. | Increased dialogue between government, industry and civil society and momentum maintained for UK EITI implementation. | UK MSG, & UK EITI Secretariat |  |  |  |  | All planned MSG meetngs have taken place, despite the global pandemic.
1.06 | Review the UK EITI MSG terms of reference and review membership of the constituencies, including lengths of service and succession planning. | 2020-05-20 | MSG to review terms of reference. Work with both industry and civil society to agree and document mechanisms for appointing new MSG members and succession planning. | More robust and relevant terms of reference. MSG has adequate membership and is quorate with robust succession arrangements. | UK MSG, & UK EITI Secretariat |  |  |  |  | Complete - MSG have reviewed terms of reference. Both industry and civil society agreed to document mechanisms for appointing new MSG members and succession planning. New Terms of Reference now available on the UK EITI website.
1.07 | Work closely with Civil Society Network to support their full return to MSG and the implementation of their new nominations process. (VALIDATION CORRECTIVE ACTIONS 1&2) | 2020-12-01 | Secretariat work closely with CSN Coordinator, once established, to ensure CSN is fully represented on MSG. The nominations process is effective and well documented and allows for representation from diverse groups. Full civil society membership is restored to MSG. | Civil society is fully engaged with EITI process, with representatives from diverse parts of civil society, so that a wide range of views are brought to the MSG. | UK EITI Secretariat/Civil Society |  |  |  |  | Secretariat worked closely with the new CSN Coordinator, to ensure CSN is fully represented on MSG. The nominations process was effective and well documented and allows for representation from diverse groups. Full civil society membership is restored to MSG. Currently trawling for new representatives from local communities. Local councils contacted in August and followed up again in early September. Secretariat and CSN coordinator to discuss next steps.
1.08 | MSG to consider gender balance in their representation in the progress towards gender parity. (2019 STANDARD - NEW REQUIREMENT) | 2020-06-01 | MSG to ensure that gender parity is taken into account in their nominations process in different constituencies. Terms of Reference include arrangements to consider gender balance. | Greater gender diversity in the MSG and greater awareness in the MSG and wider sector of the need for gender parity. | UK MSG/UK EITI Secretariat |  |  |  |  | Complete. The new Terms of Reference for each constituency include the line that they will review membership on a regular basis to consider the diversity and gender balance of its members in order to ensure that membership reflects the changing nature of the industry and the requirements of the EITI Standard
2. Promote transparent and accessible disclosure systems and good governance in the extractives sector. Enhance accountability on revenues from the UK’s extractives industries.
2.01 | Ensure that the new EITI website presents information on the extractive industries in a transparent and accessible way. | 2020-04-01 | Interactive, visually appealing content about the UK extractive industries available online that is available in a timely manner | Increased understanding of the extractive industries in the UK, greater public debate and increased interest in UK EITI. | Comms Subgroup, Sectoral Subgroup UK EITI Secretariat |  |  |  |  | Compete. Website up and running. Interactive, visually appealing content about the UK extractive industries available online that is available in a timely manner. The website is updated on a regular basis.
2.02 | Mainstreaming subgroup to take forward the recommendations of the systematic disclosure (mainstreaming) scoping study. | 2020-12-01 | The mainstreaming subgroup to produce an action plan for taking forward the recommendations of the scoping study and how any barriers to systematic disclosure can be overcome. New EITI website will collate and signpost data sources where available. MSG will consider if the reconciliation process is still required or could be made more light touch. | UK disclosure systems strengthened. The UK makes information required by the EITI Standard available through reporting systems and transparency becomes an integral and routine feature for the UK. UK EITI collates information and publishes any data that is not systmatically disclosed. UK satisfies the requirements of 2019 EITI Standard. | Mainstreaming subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | The Mainstreaming subgroup have produced an action plan for taking forward recommendations. Many of the "quick wins" are now complete i.e. new links to data and information on the website. There are still a number longer term issue that still need to be addressed, particularly in the area of mainstreaming tax data.
2.03 | Ensure that the 2019 Reconciliation and State of the Industry Report is published on time and in an accessible format | 2020-12-01 | 2019 report published on time, with information presented in an interesting and accessible way. | Enhanced accountability to the UK public on the revenues from the UK’s extractives industries. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | The MSG currently plan to publish ther 2019 Reconciliation and State of Industry report in the Autumn 2020.
2.04 | Review and agree the scope and methodology for the 2019 reconciliation process, including on gender, contract transparency and environmental reporting. | Mar/Apr 2020 | Meeting of reconciliation subgroup to discuss updates for guidance and templates, particularly in light of 2019 Standard. Need to be agreed and approved by the MSG. | An agreed methodology and approach for UK EITI reporting. Any proposals to exclude certain revenue streams are agreed by the MSG. | Reconciliation Subgroup, UK MSG & UK EITI Secretariat. |  |  |  |  | Complete. The Reconciliation subgroup agreed that they would not ask companies to provide employment data on the templates as it would add a further burden on companies.
2.05 | Improve guidance and templates to help in-scope companies report under EITI. | Mar/Apr 2020 | Reconciliation subgroup review guidance and templates to see if any improvements are needed and if any updates to template are needed to meet 2019 Standard requirements. | Increased understanding and participation from the in-scope companies in EITI reporting, more accurate completion of templates, data collection meets requirements in 2019 Standard. | UK MSG, Independent Administrator, Reconciliation Subgroup & UK EITI Secretariat. |  |  |  |  | Complete. Reconciliation subgroup have reviewed the guidance and templates to see if any improvements or updates to the reporting templates were needed to meet 2019 Standard requirements.
2.06 | Independent administrator to continue to collect information from government and companies for reconciliation. | 2020-11-01 | Complete reconciliation of payments for companies making payments over materiality threshold of £86,000. Independent Administrator presents data in an accessible manner in 2019 report and/or on UK EITI website. MSG to review after the exercise if the reconciliation effort is still needed, and/or or a more light touch method could be used as part of mainstreaming efforts. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator | 125000 | 125000 | 125000 |  | IA in process of reconciling information for 2019 reconciliation.It is expected that this information will be published in November 2020.
2.07 | Ensure that the Government's policy of disclosure of contracts and licences that govern the exploration and exploitation of oil, gas and minerals is publicly codified. (VALIDATION CORRECTIVE ACTION 5) | 2020-12-01 | Influence government bodies to ensure that government policy on each extractive licence is clearly explained. Use new EITI website to cover any gaps where necessary. Explain Government policy on publicly disclosing the full text of licences on the face of our new website, outlining any cases where they are not disclosed and why they are not. | Greater clarity on government policy on licence disclosure. Validation corrective action is addressed to ensure a revalidation assessment of "Satisfactory progress" for the UK. | Compliance Subgroup, Sectoral Subgroup |  |  |  |  | The MSG does not understand the UK Government to have a policy on the disclosure of contracts and licences that govern the extractives sector. In September 2020, the MSG agreed an approach: to be clear on our website that government does not have a specific policy on this and explain what level of information is disclosed by each organisation and where it can be found, outlining any cases where the full text of licences is not disclosed and the reasons for this. Secretariat have drafted some text and are working with the Compliance Subgroup to finalise. A new section on the UK EITI website to be added entitled "Contract and licence transparency" where all relevant information from the website will be consolidated.
2.08 | Include employment figures disaggregated by project and gender where available in 2019 report or on new website. (2019 STANDARD - NEW REQUIREMENT) | 2020-12-01 | MSG decide whether including question on gender employment on reporting templates is a proportional approach or if data in 2018 sectoral information is sufficient to meet this requirement. (The current "Extractive industries in the UK" section includes a table showing the male/female split in employment for the mining and quarrying sector for the last five years.) | Employment statistics by gender are included in future EITI reporting in line with 2019 Standard requirements. | Sectoral subgroup, Compliance Subgroup, UK EITI Secretariat and MSG |  |  |  |  | Complete. MSG decided not to include question on gender employment on reporting templates because they believe that the data included in the publicly available ONS data is sufficient to meet this requirement. This data has been used to creare current a table showing the male/female split in employment for the extractives sector for the last five years, which can be found on our website.
2.09 | Include material environmental payments by companies to government that are mandated by law, regulation or contract that governs extractive investment in 2019 report or on new website. MSG to consider if information related to ernvironmental impact and monitoring can be disclosed. (2019 STANDARD - NEW REQUIREMENT) | 2020-12-01 | MSG to consider whether the environmental payment data disclosed in 2018 sectoral information is sufficient to meet 2019 Standard requirement. (The 2018 background sectoral information included information on environmental taxes paid by the sector from 2012-18 from ONS.) | Environmental payments are included in the in the UK EITI background sectoral information in line with the 2019 Standard requirement. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | Complete - MSG agreed ONS figures on environmental taxes paid by the extractive sector as well as data from ONS on annual emissions by sector, including links and caveat to this in the background chapters should be sufficient.
2.1 | MSG to agree and publish a strategy for disclosing all contracts entered into, signed or amended from 1 January 2021. Ensure that EITI reporting describes the different types of contract and the government's policy and practice on disclosure of contracts. (2019 STANDARD - NEW REQUIREMENT) | 2020-12-01 | Secretariat draft a contract disclosure discussion paper capturing the current approach to licences by the various government agencies and any gaps in disclosure for discussion at MSG. Engagement with The Crown Estate regarding their approach to contract disclosure. | All new or amended contracts from 1st January 2021 are disclosed in line with the requirements of the 2019 Standard. Greater contract transparency in the UK extractive sector. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | Contract tracker capturing current approaches to licensing from various government agencies is included in the validation tracker. The tracker is being updated in light of discussions with the various government agencies.
2.11 | MSG to consider including additional information on the allocation of licences, such as description of procedures, actual practices and grounds for renewing, suspending or revoking. (2019 STANDARD - NEW ENCOURAGEMENT) | 2020-12-01 | The background sector chapters already provide narrative on how licensing works in the UK. This could be augmented with a link to the flow charts from the OGA. Need to look more closely at what can be done for dredging licences. | Additional information on the allocation of licences is disclosed, where available, in line with the 2019 Standard. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | Website updated to include further narrative and links on how licensing works, particularly for TCE and the Devolved Administrations.
2.12 | MSG to consider whether production and export data could be further disaggregated by region, company or project and include sources and methods of calculating volumes and values. (2019 STANDARD - NEW ENCOURAGEMENT) | 2020-12-01 | The information on both exports and production need to be disaggregated by company and project, where available. MSG can decide whether it makes sense to disaggregate the volumes and values further than required, depending on whether there is demand for more detailed information and it is feasible. | Additional data on production and export data is disclosed, where available, in line with the 2019 Standard. | Compliance Subgroup, Sectoral Subgroup UK EITI Secretariat and MSG |  |  |  |  | Complete. Additional export data and links to sources of data included on the website.
2.13 | Work with Government agencies (OGA, TCE, CES) and devolved administrations to consider the UK's licence disclosure regimes can be strengthened (VALIDATION CORRECTIVE ACTIONS 3-5) | 2020-12-01 | Information on the award and transfer of licences pertaining to companies covered in EITI reporting disclosed. | Greater contract and licence transparency and a revalidation assessment of "Satisfactory progress" for the UK. | Compliance Subgroup, Reconciliation Subgroup |  |  |  |  | Information on the award and transfer of licences by Government agencies and the Devolved Administrations updated on the website after consultation with the agencies concerned. We are working with the relevant government bodies to ensure that all necessary information is disclosed, but timing for this is uncertain and may not be complete by validation.
2.14 | The MSG to assess the materiality of mandatory social expenditures ahead of future EITI reporting ands ensure this is disaggregated by payment, nature of in-kind contributions and beneficiaries. (VALIDATION CORRECTIVE ACTION 6) | 2020-12-01 | MSG to decide if Section 106 payments are mandatory social expenditures and to highlight if these payments are material. | The recommendations from the validation are addressed and systems are put in place, where possible, to ensure that missing data etc is available and included in future reports. All recommendations are implemented to ensure a revalidation assessment of "Satisfactory progress" for the UK. | Compliance Subgroup, Sectoal Subgroup |  |  |  |  | Complete. All devolved administrations consulted and narrative and links added to website.
3. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources.
3.01 | Undertaken outreach events to spread awareness and facilitate dialogue about EITI and the UK extractive industries. (VALIDATION CORRECTIVE ACTION 7) | 2020-12-01 | Communications Subgroup to make recommendations for MSG to action and take forward, including organising one-off events, participation at key industry and international EITI events, articles in trade publications, quarterly newsletters and better use of social media. | Greater awareness and understanding of EITI and its importance to the transparency agenda. Increased industry and public awareness of the work of the UK EITI MSG. | Comms subgroup, UK EITI Secretariat. |  |  |  |  | Two awareness raising events were arranged for April and May 2020. They were both subsequently postponed due to the global pandemic. Virtual launch event for the Reconciliation and State of Industry report to take place on 9th December 2020, to include Lord Callanan and speakers from civil society and industry. Invites to be sent to industry, civil socierty and government stakeholders. The UK Secretariat has also participated in virtual awareness-raising events organised by other organisations. The new website launched in May 2020 and is a key part of our awareness-raising efforts.
3.02 | Establish an independent UK EITI website that presents information in a more interactive and accessible way and allows for more timely updates. | 2020-05-01 | A fully accessible independent UK EITI website with interactive data on the extractive industries and links to other relevant data sources. Website will include information about EITI and the work of the MSG with relevant sections covering both industry and civil society. Website must comply with government accessibility criteria. | The UK EITI website will be used by the industry and the public to source data for the extractive industries in the UK, thus enriching public debate. The website will be easier to update than the current website, leading to more timely data. The website will be the first step in the UK's move towards systematic disclosure/mainstreaming, with links to relevant data sources and further information on the sector. | Comms subgroup, UK EITI Secretariat. | 47000 | 10000 |  |  | Complete. The website was launched at the end of May 2020.
3.03 | Organise launch event for new UK EITI independent website to raise awareness of the new website and UK EITI more broadly. Work with BEIS comms and MSG consitituencies to advertise launch and target the audience. | 2020-04-01 | Launch event in London/Aberdeen, with good attendance from industry, civil society and government. Develop good programme of speakers and possible Ministerial participation. | Increased awareness of UK EITI and its new website across government, industry and civil society and greater use of the new EITI website. | Comms subgroup, UK EITI Secretariat. | 3000 |  |  |  | Both events had to be postponed in light of the global pandemic.
3.04 | MSG members to promote and stimulate interest in EITI within their industry. Use MSG member networks to promote EITI report. | 2020-12-01 | MSG members to use/reference EITI in their own publications/websites, events and consultation responses. Dissemination of the report to a wider audience via events, websites and social media. | Increased understanding of EITI within industry and its importance to the transparency agenda.Report is used as a tool to improve debate on extractive industry issues. | Communications subgroup and all MSG members |  |  |  |  | Members have ensured that information on the planned awareness raising events and new website were disseminated to their stakeholders and contacts. UK EITI has also been promoted via industry and civil society websites and social media platforms.
3.05 | Appoint a UK EITI Champion | 2020-02-01 | Submission to minister or senior official inviting them to take on the role of the UK EITI Champion. | New UK EITI Champion in place by Spring 2020 to further build awareness of UK EITI. | UK EITI Secretariat |  |  |  |  | Complete. Lord Callanan was appointed the new UK EITI Champion in July 2020 and has been regularly briefed on EITI progress.
4. Contribute to international efforts to further transparent and accessible disclosure systems, common global reporting standards and good governance in the extractives sector.
4.01 | Participate in EITI calls with other implementing countries to share experiences of EITI implementation. | Ongoing | Share EITI experience with other countries via webinars and participation in conferences organised by EITI International Secretariat. | Other implementing countries or countries considering implementation learn from UK experience. The UK learns from other implementing countries to ensure more effective implementation in the UK. | UK EITI Secretariat |  |  |  |  | Secretariat have held regular meetings with colleagues from the secretariats in Germany and the Netherlands. Secretariat have had ad-hoc contact with other countries such as Trinidad and Tobago, Mongolia and will be participating in a workshop on mainstreaming organised by the Columbian Secretariat in September.
4.02 | Secretariat and MSG members to attend events organised by the International Secretariat to share UK experience and build connections with other implementing countries | Ongoing | Share EITI experience with other countries via webinars and participation in conferences organised by EITI International Secretariat. | Greater connections between UK EITI and other implementing countries to enable better knowledge sharing and more effective implementation. UK more aware of latest developments in EITI Standard and examples of best practice. | UK EITI Secretariat, MSG members | 5000 | 5000 | 5000 |  | Participation at by the UK Secretariat at the EITI Board meeting in Oslo in February 2020.
4.03 | Participate in regular calls with the EITI International Secretariat to share experiences of UK implementation in order to inform the development of the EITI Standard. | Ongoing | Share UK experience with International Secretariat, clearly communicating UK priorities for the development of the Standard. | Development of Standard informed by UK implementation experience and expertise. | UK EITI Secretariat |  |  |  |  | UK Secretariat in regular contact with the International Secretariat, particularly with regard to process changes brought about by the global pandemic and its impact on revalidation and reporting.
RAG rating code
Complete
On track for delivery by agreed timeline
Medium risk not on track for delivery by agreed timeline
High risk not on track for deliver by agreed timeline

## Raising public awareness (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
2. Increase public understanding of the social and economic impacts of the UK's extractive industries and enrich public debate on the governance and stewardship of the UK's oil, gas and mineral resources. | Precondition - Functions legislation to allow HMRC to engage in EITI. | 1. Lack of awareness on the extractive industries in the UK. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.1 Establish a Validation subgroup to take forward the recommendations of the validation report and look at requirements to gain full compliance. | Subgroup to make recommendations for MSG to action and take forward. | UK EITI addressed issues that validation team highlighted and UK applies again to become a fully compliant country. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  |  | 1.2 Hold post-validation outreach event to provide stakeholders with an update on progress & restate UK's commitment to EITI. Possible Ministerial attendance. | Event aimed at communicating with a wider audience. | Increase awareness and support for UK implementation of EITI in the UK. | UK MSG & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.3 Hold or participate in events to raise awareness of UK EITI. Possible Ministerial/UK EITI MSG attendance. | Events aimed at raising awareness of EITI and its importance to industry and the transparency agenda. | Industry awareness of UK EITI and the work of the MSG increased. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.4 Establish an independent UK EITI website. | An independent UK EITI website with links to the relevant and up to date data. Approved by the Government Digital Service (GDS). | The UK EITI website will be the website used by the sector to source data for the industry. UK EITI moves towards systematic disclosure. | UK MSG & UK EITI Secretariat. | 2019-12-01 | 30000 |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Draft a tender for contract for establishing nrw UK EITI independent website. |  |  | UK Secretariat, BEIS Procurement and Finance, UKSBS and MSG | 2019-12-01 |  |  |  |  | Pending
|  | 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.6 Use range of communication channels to ensure that all companies within scope of UK EITI are aware of the need to report. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | July/August 2019 |  |  |  |  | On-going
|  | 3. Current inconsistent production of data. | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 1.7 Improve guidance and templates to help in-scope companies report under EITI. | Updated industry guidance notes and templates, e-mails, websites, articles in trade magazines, possible webinar event. | Increase understanding and participation from the in-scope companies. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-06-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Set up a subgroup to take forward the recommendations of the systyematic disclosure (mainstreaming) scoping study. | Scoping study by BEIS analysts in consultation with MSG members. | The UK EITI makes information required by the EITI Standard vailable through reporting systems and transparency becomes an integral and routine feature for UK EITI. | UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.9 Independent administrator to collect information from government and companies for reconciliation | Complete reconciliation of payments. | Independent third party reconciliation will add weight to the tax payment figures put into the public domain. | Independent Administrator, HMRC, Oil and Gas Authority, The Crown Estate, Crown Estate Scotland, UK MSG & UK EITI Secretariat. | July/August 2019 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 1.10 Review and agree the scope and methodology for the 2018 reconciliation process. | Meeting of reconciliation subgroup to discuss updates for guidance and templates. Need to be agreed by the MSG. | An agreed methodology and approach for UK EITI reporting. Proposals to exclude certain revenue streams need to be revisited and agreed by the MSG. | UK MSG & UK EITI Secretariat. | 2020-03-01 |  |  |  |  | Ongoing

## Accessibility of information (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
3. Ensure information is readily accessible and presented to the public in a clear manner. | Precondition- All stakeholders need to be engaged on EITI and need to have a good understanding of the extractives industry on the UK - Need an informed and engaged MSG -Expertise needed on presentation of the data. | 1. Lack of awareness on the extractive industries in the UK. 2. Information is currently not consolidated and is published through a variety of means and agencies. | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.1 Ensure that both the UK EITI gov.uk and independent UK EITI website is updated in a timely manner to provide relevant information | UK EITI website updated when there are changes in MSG membership and new documents to upload. | Valuable information source for stakeholders leading to increased understanding and awareness of UK EITI. | UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.2 Use MSG members to ensure that the report content is accessible to multiple audiences | UK EITI website updated and the annual report is available in accessible format as required by the Gov.UK website. | Maximise audience of EITI report and comply with Gov.UK regulations. | UK EITI Secretariat | Nov-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.3 Ensure the report is written in plain English | Increased support and understanding amongst key stakeholder groups | Increase understanding and awareness of UK EITI and ensure messages resonate with industry, civil society and Government representatives. | Sectoral subgroup, with review by MSG | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.4 Consider and agree the presentation of EITI reports. Short reconciliation report and "State of Industry" chapter with a number of standalone background chapters. | Access to a range of data that can be manipulated | Increase understanding of the extractive industries in the UK and encourage debate. | UK MSG & UK EITI Secretariat | Sept-Dec 2019 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 2.5 Publish Annual Progress report | Overview of the work of the MSG in 2018. | Increase understanding and awareness of the work of the MSG. | UK MSG & UK EITI Secretariat | 2019-07-01 |  |  |  |  | Pending
|  |  | Requirement 4: Revenue Collection - 4.9 Data Quality | 2.6 Independent administrator to present EITI report to the MSG to consider and endorse before publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG, Independent Administrator & UK EITI Secretariat. | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.7 MSG to agree EITI report ahead of publication | Annual EITI report | MSG supports and has confidence in EITI report and is willing to promote it. | UK MSG & UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.8 Agree communications plan to promote the published report | Comms subgroup to draw up a communications workplan to promote UK EITI report and other activities. | Maximise audience of EITI report | Communications sub group & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.9 Publication of annual EITI report | Publish report in timely manner. | Report is used as a tool to improve debate on extractive industry issues | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.10 Use MSG member networks to promote EITI report | Dissemination of the report to a wide audience | Report is used as a tool to improve debate on extractive industry issues | Communications sub group, UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 2.11 During outreach, consult stakeholders on how to present information e.g. are the new summary report and standalone chapters an improvement? | Comments received during outreach activities | A record of outreach and comments received is maintained that should be reviewed regularly | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 2.12 Targeted communications to specific civil society groups to raise awareness of the EITI report | Increase awareness of the EITI report | Stimulate debate on the UK extractive industries | Communications sub group and UK EITI Secretariat | 2019-11-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.1 Monitor the need for training activities, workshops etc. for MSG members | Various training activities | Increase MSG understanding of the extractive industries in the UK and identify next steps for implementation | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.2 Invite representatives from other countries to attend MSG meetings and share UK's and their experiences. | Share experiences with colleagues from overseas. | Increased understanding of options to implement EITI for UK and other countries sharing good practice. | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 3.3 Use MSG membership to promote and stimulate interest in EITI within their industry. | MSG members to use/reference EITI in their own publications/websites and consultation responses | Increased understanding of EITI within industry and its importance to the transparency agenda | UK MSG | 2020-03-01 |  |  |  |  | On-going

## Support of transparency (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
4. Support the UK government’s championing of extractives transparency and open government | Precondition- The profile of EITI needs to be raised and more needs to be done to promote what the UK is doing with implementation. Reliant on all companies complying with EITI. | 1. Only budget to cover costs of report and possible launch activity around publication. 2.DFID is responsible for international influencing. 3. Lack of awareness of EITI. | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.1 Allow nominated people to attend MSG meetings | Increase the pool of people that can attend MSGs while retaining a smaller MSG that concentrates on participation | Create an inclusive and open MSG to increase support of EITI and strengthen knowledge base of MSG members | UK EITI Secretariat & UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.1 Public Debate | 4.2 Participate in EITI calls with other developed countries to share experiences | Share EITI experience with other countries via webinars and conferences organised by EITI International Secretariat. | Expand understanding of options to implement EITI for UK and other countries | UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.2 Company Engagement | 4.3 Consider methods to encourage good practice by companies | Disseminate information on good practice by companies | Helping to share good practice | UK MSG & UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.3 Civil Society Engagement | 4.4 Re-engage with Civil Society Network (CSN) with view to encouraging them to return to the MSG. | Work closely with CSN colleagues to agree a return date to the MSG. | The return of CSN to the MSG | UK EITI Secretariat | 2019-11-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.5 Review the UK EITI MSG terms of reference. | Work with BEIS legal team to review current terms of reference. | More robust and relevant terms of reference | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Pending
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 4.6 Review membership of the constituencies, including lengths of service and succession planning. | Work with both industry and civil society to agree updated mechanisms for appointing new MSG members and succession planning. | Ensure that the MSG has adequate membership and is quorate with robust succession arrangements. Industry has agreed a plan and a process is now in place. | UK MSG, UK EITI Secretariat & BEIS Legal | 2020-04-01 |  |  |  |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.3 Lessons learned and follow up on recommendations | 4.7 Independent administrator to make recommendations for future reconciliation processes | Generate suggestions to improve reconciliations | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive. UK EITI to benefit from continuous improvement | Independent Administrator | 2019-12-01 |  |  |  |  | Pending
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 4.8 Review outcome and impacts on EITI implementation | Lessons learned on UK EITI | Ensure EITI is beneficial to stakeholders and the information produced is comprehensive and readily accessible to stakeholders and UK benefits from continuous improvement. | UK MSG & UK EITI Secretariat | 2019-12-01 |  |  |  |  | On-going
|  |  | Requirement 2: Contracts and licenses - 2.5 Beneficial Ownership | 5.1 Monitor and consider existing and upcoming transparency initiatives in the UK EG Chapter 10 Accounting Directive, Transparency Directive and Register of Beneficial Ownership | Ensure that UK EITI is consistent with other transparency initiatives | UK EITI will reflect other reporting requirements to ensure any additional requirements are proportionate. | UK Government and extractive companies in scope | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.1 Regular meetings of the MSG | Hold MSG meetings every 2 months to ensure speedy and effective implementation | Strengthen the participative multi stakeholder process of EITI and increase confidence among stakeholders | UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.2 Assess and outline plans to address any potential capacity restraints in Government agencies, companies and civil society organisations that may be an obstacle to implementation | MSG to consider and take steps to remove capacity constraints | Ensure speedy and effective implementation | UK MSG and UK EITI Secretariat | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.4 MSG Functioning | 6.3 Ensure that any updates to the EITI Standard in 2019 are understood and preparations are made to ensure that any new Standards are adopted. | MSG to discuss new Standard with EITI International. | The 2018 UK EITI report reflects changes to the EITI Standard for 2019. | UK MSG, UK EITI Secretariat and EITI International Sercretariat. | 2019-09-01 |  |  |  |  | On-going
|  |  | Requirement 1: MSG Oversight - 1.5 Work Plan | 6.4 Agree and maintain and current work plan, fully coasted and aligned with the reporting and validation deadlines established by the EITI Board | Up to date UK EITI work plan | Provides direction to the MSG on what areas UK implementation should focus on | UK EITI Secretariat and UK MSG | 2020-03-01 |  |  |  |  | On-going
|  |  | Requirement 7: Outcomes and Impact - 7.4 Outcomes and impact of EITI implementation on natural resource governance | 6.5 Agree and publish annual progress report | Lessons learned on UK EITI | Continuous improvement | UK EITI Secretariat and UK MSG | 2019-07-01 |  |  |  |  | On-going

## IA Appointment (hidden)
Prioritized objectives (explained) | Context: Preconditions and Risks | Capacity constraints | Sub headings & EITI requirement addressed | Activities | Expected Output | Expected Outcome | Responsible Entity | Timeline | Cost |  |  |  | Status
[9 empty] | 2019/20 | 2020/21 | 2021/22 | 2022/23
1. Appointment of a new Independent Administrator. | Precondition - Independent Administrator needs to be appointed by June 2019 to ensure that the guidance and templates are circulated and made available on the UK EITI website for in-scope companies. Risk - The IA is not in place in time, therefore delaying the 2018 reporting process. | The current contract ran out on 28th February 2019. | Requirement 1 - Oversight by the multi-stakeholder group. 1.4 Multi-stakeholder group. | 1.1 Evaluation panel set up to look at and score bids received from potential IA's. Interviews to take place for highest scoring bids and evaluation panel to select the new IA. | MSG to evaluate and score all tenders and select best candidate for role of IA. | IA appointed in time for the start of the 2018 process in June 2019. | UK MSG and UK EITI Secretariat. | 2019-06-01 | 126000 | 126000 | 126000 |  | Ongoing
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.5 Research and present information on the legal framework for oil and gas in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.6 Research and present information on the legal framework for mining in the UK for the contextual section of the EITI report | Annual EITI report | Publication of an EITI report that improves public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.7 Research and present information on the fiscal regime in the UK for oil and gas sector for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.8 Research and present information on the fiscal regime in mining industry for the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.9 Research and present information giving an overview on the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (oil and gas) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.11 Research and present information giving an overview on the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries (mining) | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.12 Research and present information on the contribution to the economy from the oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.13 Research and present information on the contribution to the economy from the mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.14 Research and present information on production data for oil and gas sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UK MSG & UK EITI Secretariat | [5 empty] | Completed
|  |  | Requirement 7: Outcomes and Impact - 7.2 Data Accessibility | 1.15 Research and present information on production data for mining sector in the UK for the contextual section of the EITI report | Annual EITI report | Improve public understanding and debate of the extractive industries | UKM MSG & UK EITI Secretariat | [5 empty] | Completed