## Sheet1
Implementation Plan 2023
Communication & Engagement Strategy (C&E)
updated 5 May
Activities | Status | Lead Implementer
Preparing for New EITI Standard |  | Jan - June 2023
April-May | 2023
Maintaining and Improving current C&E
Build relevance, accessibility of UK EITI website
Prioritise pages for update, including Energy Transition page | Ongoing | Tim, Mike
Prepare analysis, synthesis, graphics = content more user friendly | Ongoing | Tim, Mike, sub-group(s)
Understand latest HMG (Govt Digital Service- GDS) requirements for (People Living w Disabilities (PLWD) | None | UK Secretariat
Invite HMG experts to advise on considerations, scoping, cost, etc | None completed | UK Secretariat
Prepare for & boost event participation, host dialogue opportunities
Compile/update 2023 events calendar | Completed | Tim, Mike, sub-group(s)
Prioritise events, seek/plan external event participation | None | C&E sub-group, MSG
Draft proposals for Innovation Talks at EITI Global Conference | Completed | Mike, Tim, interested members
Prepare stakeholder-specific messaging on UK EITI relevance to Just Energy Transition (JET) & how data can be used in public debate on JET issues | None | Tim, Mike, sub-group(s)
Prepare/Update slide decks, leaflets, other materials on UK EITI relevance to energy transition | Ongoing | Tim, Mike, sub-group(s)
Prepare list of prio stakeholders - renewables, essential minerals - industry, HMG, CSO, local councils, MPs | Ongoing | Tim, Mike, sub-group(s)
Meet w DESNZ comms teams to discuss collaboration opportunities, key contacts - including media & monitoring | None | UK Secretariat
Presentation for extractives MPs on UK EITI, Standard | Completed | UK Secretariat
Consider activities for UK participation at EITI Global Conference June 2023 | Completed | UK Secretariat
Implementing the 2023 EITI Standard |  | July - Dec 2023
June-July | 2023
Build understanding of new requirements & opportunities
Update sector-specific guidance materials to explain the new Standard and reporting requirements | Completed | UK Secretariat, BDO, sub-groups
Make presentations, convene working seminars, host individual mtgs | Completed | UK Secretariat
Identify/contact key media, journalists w interest in extractives, renewables, governance; invite to roundatble on UK EITI | None | Tim, Mike, sub-group(s), DESNZ
Prepare for & boost event participation, host dialogue opportunities
C&E, MSG review draft slide decks, leaflets, etc. | Ongoing | Tim, Mike, sub-group(s)
Incorporate C&E, MSG input/feedback & Finalise | None | Mike, Tim
Prepare bespoke materials for events | None completed? | Mike, Tim
Update 2021 mapping of Energy Transition Activities
Review mapping, research current landscape | None | Tim, Mike
Prepare recommendations for MSG approval | None | Tim, Mike
Energy Transition subgroup
Prepare Concept Note for MSG | Ongoing | Tim, Mike
Prepare ToR, recruit members | None | Mike, Tim
Build relevance, accessibility of UK EITI website
Consult PLWD groups re: priority functions, scope, content | None | Mike, Tim
Secure funds, Prepare ToR for site-builder | Ongoing | Mike, UK Secretariat
Finish updates to content, graphics, etc | Ongoing | Mike, Tim, UK Secretariat (BDO?)
Scoping study: revenue materiality - renewables, essential minerals
Contract/conduct scoping study if approved by MSG | Ongoing | UK Secretariat, BDO?
August - September |  | 2023
Build understanding of new requirements & opportunities
Distribute guidance documents, convene working seminars/individual mtgs | Completed | UK Secretariat
Build relevance, accessibility of UK EITI website
Procure site-builder for PLWD accessibility | Completed | UK Secretariat
Approve workplan, design/functionality | Completed | MSG
Event participation, host dialogue opportunities
Make presentations, convene working seminars, individual mtgs | Completed | UK Secretariat
Energy Transition subgroup
Convene 1st meeting | n/a | UK Secretariat
October - November |  | 2023
Build accessibility of UK EITI website
Testing and launch of PLWD accessibility features functions | Ongoing | UK Secretariat, contractor
Event participation, host dialogue opportunities
Make presentations, convene working seminars, individual mtgs | Completed | UK Secretariat
Scoping study: revenue materiality - renewables, essential minerals
Prepare Concept Note for MSG consideration/approval | n/a | Tim, Mike
December |  | 2023
Event participation, host dialogue opportunities
Make presentations, convene working seminars, individual mtgs | Completed | UK Secretariat
Ongoing & Recurring activities |  | April - Dec 2023
Track, publicise consultations relevant to UK EITI | Ongoing | UK Secretariat
Update website | Ongoing | UK Secretariat
Prepare Annual Report, consultations | Ongoing | UK Secretariat
Sub-group mtgs: C&E, Sectoral, Energy Transition, | Ongoing | UK Secretariat, Tim, BDO
Liaise w HMG, industry, CSO colleagues | Ongoing | UK Secretariat
Note on A57: Tim Vickery: suggested by Mark Burnett EITI Oslo
Note on A81: Tim Vickery: suggested by Mark Burnett EITI Oslo